## Sheet1
Name | Description | Estimated Time Requirement
Player and AI progmon selection menu/interface | Feature that allows the user to select the progmon the player and AI will battle with. | 2 hours
Battle menu/interface | The primary interface of the game. This display allows the user to interact with the battle through the options to fight, bag, progmon, or quit. | 2 hours
Basic "Fight" Option | The player's choice to fight attacks the enemy progmon with automatic progmon attack selection. | 2 hours
Basic "Bag" Option | The player's choice to bag allows them to use an item. Initially limited to the use of a health potion. | 2 hours
"Quit" Option | The player's choice to quit closes the game. | 1 hour
Progmon Numeric Health Display | The battling progmons' current health is displayed to the user as an integer. | 1 hour
Basic AI battle tactics | The AI's basic decisionmaking in battle. It can choose to fight, bag, or run based on specified conditions. | 1 hour
Initial Progmon options: Electric Cat and Fire Dragon | The first two progmon options. Each requires unique attack definitions, AI attack handling, and sprite work. | 4 hours
"Fight" Option Attack Selection | A menu allowing the player to select the specific attack their progmon will use when choosing to fight. 4 attack options. | 3 hours
"Bag" Option Item Selection | A menu allowing the player to select an item they wish to use when choosing to open their bag. | 2 hours
Additional Item Options | More items to select from. (e.g. progmon reviver) | 3 hours
"Progmon" Option Implementation | A menu allowing the player to switch the progmon they are using to battle. | 3 hours
Battle Sound Effects | Addition of sounds that signal a progmon has attacked and/or taken damage. | 3 hours
Battle Animations | Animations the signal a progmon has attacked and/or taken damage. | 4 hours (highly dependent on desired quality)
Progmon Health Bar | Progmon health is displayed with an updating HP bar | 3 hours
Progmon Battle Statistics and Types | Unique statistics that impact each progmon's battle capability. Progmon types, attack speed, attack rating, defense rating, special attacks/defenses | 15 hours
Additional Progmon Options | More progmon to select from. | 3 hours per progmon
AI Difficulty Options | Alternative settings for the difficulty of the AI. Harder difficulties should have improved decisionmaking. | 6 hours
Cheat: Instant Kill | The enemy progmon is instantly defeated. | 2 hours
Cheat: Max Health | The player's progmon is restored to its maximum health. | 2 hours
Cheat: God Mode | The player's progmon becomes invulnerable to damage from its enemy. | 2 hours
Stage/Battleground background | A background for the progmon battle screen. | 1 hour
Perspective Based Sprites | Additional sprites for each progmon that display their form from different perspectives | 1 hour per progmon
Keyboard-Based User Input Option | The player is able to make their battle decisions using the arrow keys and a couple keys assigned to "A" and "B" | 6 hours
Battle Feedback Display | Pop-up displaying information about the events of the battle. Gives the player information about what attack occurred and whether or not it succeeded. | 4 hours