## Sheet1
Name | Description | Estimated Time Requirement
Player and AI progmon selection menu/interface | Feature that allows the user to select the progmon the player and AI will battle with. | 2 hours
Battle menu/interface | The primary interface of the game. This display allows the user to interact with the battle through the options to fight, bag, progmon, or quit. | 2 hours
Basic "Fight" Option | The player's choice to fight attacks the enemy progmon with automatic progmon attack selection. | 2 hours
Basic "Bag" Option | The player's choice to bag allows them to use an item. Initially limited to the use of a health potion. | 2 hours
"Quit" Option | The player's choice to quit closes the game. | 1 hour
Progmon Numeric Health Display | The battling progmons' current health is displayed to the user as an integer. | 1 hour
Basic AI battle tactics | The AI's basic decisionmaking in battle. It can choose to fight, bag, or run based on specified conditions. | 1 hour
Initial Progmon options: Electric Cat and Fire Dragon | The first two progmon options. Each requires unique attack definitions, AI attack handling, and sprite work. | 4 hours